## Scope
Client Name | HDFC ERGO GENERAL INSURANCE
Program Name | HDFC ERGO - Unified Claims
Project Name | HDFC ERGO - Unified Claims
Products
Variants
Transactions
Definition of Test & Scope
UAT
Sanity
Regression
Performance
Components | Total | Positive / UI | Negative
PA_PolicySearch | 146 | 134 | 12
PA_PolicyBasicDetails | 128 | 122 | 6
PA_PolicyHospitalDetails | 121 | 97 | 24
SI_Dashboard | 75 | 62 | 13
SR_Dashboard | 40 | 35 | 5
SI_NewUser | 136 | 83 | 53
SI_ModifyUser | 59 | 48 | 11
SI_Activate | 51 | 32 | 19
SI_Deactivate | 42 | 24 | 18
SI_ModifyRole | 145 | 119 | 26
SR_NewUser | 45 | 27 | 18
SR_Activate | 78 | 52 | 26
SR_Deactivate | 80 | 44 | 36
SI_ModifyDetail | 164 | 86 | 78
Total | 1310 | 965 | 345

## Deliverables
Test Deliverables for testing |  | Frequency
Test Strategy & Plan |  | Release level
RTM |  | User Story level
End to End level
Requirement Analysis |  | Release level
Automation Test Scripts |  | Modular
Sanity
Regression
Full Regression
Performance Test Scripts |  | Early PT
Full PT
DSR |  | Daily
WSR |  | Weekly
Sanity Report |  | Deployment level / Once a week
Lean Regression |  | Weekly
Full Regression |  | Before Major Release
Early PT |  | Weekly
Full PT |  | Release level
Defect Triage Report |  | Twice a week
Sprint End Report |  | POD1 |  |  | POD2 |  |  | POD3
| Sprint 1 | Total User Stories Planned | Completed | Remarks | Total User Stories Planned | Completed | Remark | Total User Stories Planned | Completed | Remark
|  | 5 | 5 | 0 | 3
| Sprint 2 | 6 | 2 | Remaining moved sprint 4 No Sign off recieved | 8
| Sprint 3 | 0 | 0 | Sprint 2 Feedbacks and API integrations are taken | 6

## Others
Pre-req
Sr. No | Pre-Reqs | Status | Remarks (if any)
1 | JIRA Project Access for Requirements | Done
Test Environment | URLs
QA
UAT
Entry Criteria
All the user stories should be Deployed to the QA environment
Exit Criteria
System should be up and running Test case executed with No major bugs

## Assumption
Assumption taken
1. User stories are covered all the edge scenario
2. We are assuming as : We are getting enough time to test the user stories in the future by considering the tentative dates mentioned as August 1st.

## Test Plan
Health Claims Project Charter
|  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  |  | October |  |  |  |  | November |  |  |  |  | December
Project Phase | Progress | RAG | 05 May - 09 May | 12 May - 16 May | 19 May - 23 May | 26 May - 30 May | 02 June - 06 June | 09 June - 13 June | 16 June - 20 June | 23 June - 27 June | 30 July - 04 July | 07 July - 11 July | 14 July - 18 July | 21 July - 25 July | 28 Aug - 01 Aug | 04 Aug - 08 Aug | 11 Aug - 15 Aug | 18 Aug - 22 Aug | 25 Aug - 29 Aug | 30 Aug 3 Sept | 04 sept- 08 sept | 11 Sept - 15 Sept | 18 Sept - 22 Sept | 25 Sept- 29 Sept | 30 Sept 3 Oct | 04 Oct- 08 Oct | 11 Oct - 15 Oct | 18 Oct- 22 Oct | 25 Oct- 29Oct | 30 Oct 3 Nov | 04 Nov- 08 Nov | 11 Nov- 15 Nov | 18 NOv- 22 Nov | 25 Nov- 29 Nov | 30 Nov 3 Dec | 04 Dec - 08 Dec | 11 Dec - 15 Dec | 18 Dec - 22 Dec | 28 Dec- 31 Dec
EBV Testing
* Requirment Analysis | 100% | Done | Requirement Analysis
* Test Design | 80% | In Progress | Test Design
* Functional Test Execution | Not Started
* API Testing (X APIs) | Not Started | [25 empty] | API Manual Test Execution
* End to End Testing | Not Started | [14 empty] | End to End Test Execution
* EBV Test Closure | Not Started | [9 empty] | EBV Test Closure
QA Support
* Test Execution Support to UW & Ops | [5 empty] | Co - Testing Duration with UW & Ops
* QA Defect Analysis | [33 empty] | Business UAT Defect Analysis
* QA Sign Off | [38 empty] | Sign-off & Go-LIVE

## Status Report
Status Report As on | June 17th , 2025
OverAll Scope
UCP- Health : User Story Wise |  |  |  | Functional
Components | Total | Functional | Technical | Available for Test Design |  |  | Dev Pending US
Total | 0 | 0 | 0 | 0 |  |  | 0
Test Design Status
| Userstory Level count |  |  | Till Date Design Count
Track | Total | Done | Pending | Total Testcases |  | Proportional Weightage |  | Weightage
PA_PolicySearch | 146 |  |  | 146 | 146
PA_PolicyBasicDetails | 128 |  |  | 128 | 128
PA_PolicyHospitalDetails | 83 |  |  | 83 | 83
SI_Dashboard | 75 |  |  | 75 | 75
SR_Dashboard | 40 |  |  | 40 | 40
SI_NewUser | 136 |  |  | 136 | 135
SI_ModifyUser | 59 |  |  | 59 | 59
SI_Activate | 51 |  |  | 51 | 51
SI_Deactivate | 42 |  |  | 42 | 42
SI_ModifyRole | 145 |  |  | 145 | 171
SR_NewUser | 45 |  |  | 45 | 46
SR_Activate | 78 |  |  | 78 | 83
SR_Deactivate | 80 |  |  | 80 | 80
SI_ModifyDetail | 164 |  |  | 164 | 163
Total | 1272 | 0 | 0 | 1272 |  | 0% |  | 0%
Test Execution Status
Userstory Level Execution Count
Test Execution | Total | Pass | Fail | Blocked | On-Hold | Pending | NA
NO TEST CASES EXECUTED AS THERE IS NO ENVIRONMENT
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0