## Test Plan
Health Claims Project Charter
POD1 | Sprint 1 |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  |  | October |  |  |  |  | November |  |  |  |  | December
| Project Phase | Progress | RAG |  | 05 May - 09 May | 12 May - 16 May | 19 May - 23 May | 26 May - 30 May | 02 June - 06 June | 09 June - 13 June | 16 June - 20 June | 23 June - 27 June | 30 July - 04 July | 07 July - 11 July | 14 July - 18 July | 21 July - 25 July | 28 July - 01 Aug | 04 Aug - 08 Aug | 11 Aug - 15 Aug | 18 Aug - 22 Aug | 25 Aug - 29 Aug | 30 Aug 3 Sept | 04 sept- 08 sept | 11 Sept - 15 Sept | 18 Sept - 22 Sept | 25 Sept- 29 Sept | 30 Sept 3 Oct | 04 Oct- 08 Oct | 11 Oct - 15 Oct | 18 Oct- 22 Oct | 25 Oct- 29Oct | 30 Oct 3 Nov | 04 Nov- 08 Nov | 11 Nov- 15 Nov | 18 NOv- 22 Nov | 25 Nov- 29 Nov | 30 Nov 3 Dec | 04 Dec - 08 Dec | 11 Dec - 15 Dec | 18 Dec - 22 Dec | 28 Dec- 31 Dec
| * Requirment Analysis | 100% | Done |  | Requirement Analysis
| * Test Design | 80% | In Progress |  |  | Test Design
| * Functional Test Execution | Not Started | [15 empty] | Test Case Execution
| * API Testing (X APIs) | Not Started | [17 empty] | API Testing
| * End to End Testing | Not Started | [15 empty] | End to End Testing
UAT Support
* UAT Defect Analysis
* UAT Sign Off
| Sprint 2 |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  |  | October |  |  |  |  | November |  |  |  |  | December
| Project Phase | Progress | RAG | 05 May - 09 May | 12 May - 16 May | 19 May - 23 May | 26 May - 30 May | 02 June - 06 June | 09 June - 13 June | 16 June - 20 June | 23 June - 27 June | 30 July - 04 July | 07 July - 11 July | 14 July - 18 July | 21 July - 25 July | 28 July - 01 Aug | 04 Aug - 08 Aug | 11 Aug - 15 Aug | 18 Aug - 22 Aug | 25 Aug - 29 Aug | 30 Aug 3 Sept | 04 sept- 08 sept | 11 Sept - 15 Sept | 18 Sept - 22 Sept | 25 Sept- 29 Sept | 30 Sept 3 Oct | 04 Oct- 08 Oct | 11 Oct - 15 Oct | 18 Oct- 22 Oct | 25 Oct- 29Oct | 30 Oct 3 Nov | 04 Nov- 08 Nov | 11 Nov- 15 Nov | 18 NOv- 22 Nov | 25 Nov- 29 Nov | 30 Nov 3 Dec | 04 Dec - 08 Dec | 11 Dec - 15 Dec | 18 Dec - 22 Dec | 28 Dec- 31 Dec
| * Requirment Analysis | 100% | Done |  | Requirement Analysis
| * Test Design | 80% | In Progress |  |  |  | Test Design
| * Functional Test Execution | Not Started | [18 empty] | Test Case Execution
| * API Testing (X APIs) | Not Started | [20 empty] | API Testing
| * End to End Testing | Not Started | [18 empty] | End to End Testing
UAT Support
* UAT Defect Analysis
* UAT Sign Off
| Sprint 3 |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  |  | October |  |  |  |  | November |  |  |  |  | December
| Project Phase | Progress | RAG | 05 May - 09 May | 12 May - 16 May | 19 May - 23 May | 26 May - 30 May | 02 June - 06 June | 09 June - 13 June | 16 June - 20 June | 23 June - 27 June | 30 July - 04 July | 07 July - 11 July | 14 July - 18 July | 21 July - 25 July | 28 July - 01 Aug | 04 Aug - 08 Aug | 11 Aug - 15 Aug | 18 Aug - 22 Aug | 25 Aug - 29 Aug | 30 Aug 3 Sept | 04 sept- 08 sept | 11 Sept - 15 Sept | 18 Sept - 22 Sept | 25 Sept- 29 Sept | 30 Sept 3 Oct | 04 Oct- 08 Oct | 11 Oct - 15 Oct | 18 Oct- 22 Oct | 25 Oct- 29Oct | 30 Oct 3 Nov | 04 Nov- 08 Nov | 11 Nov- 15 Nov | 18 NOv- 22 Nov | 25 Nov- 29 Nov | 30 Nov 3 Dec | 04 Dec - 08 Dec | 11 Dec - 15 Dec | 18 Dec - 22 Dec | 28 Dec- 31 Dec
| * Requirment Analysis | TBD
* Test Design
* Functional Test Execution
* API Testing (X APIs)
* End to End Testing
UAT Support
* UAT Defect Analysis
* UAT Sign Off
POD 2 | Sprint 1 |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  |  | October |  |  |  |  | November |  |  |  |  | December
| Project Phase | Progress | RAG | 14 Apr - 18 Apr | 21 Apr - 25 Apr | 28 Apr - 02 Apr | 05 May - 09 May | 12 May - 16 May | 19 May - 23 May | 26 May - 30 May | 02 June - 06 June | 09 June - 13 June | 16 June - 20 June | 23 June - 27 June | 30 July - 04 July | 07 July - 11 July | 14 July - 18 July | 21 July - 25 July | 28 July - 01 Aug | 04 Aug - 08 Aug | 11 Aug - 15 Aug | 18 Aug - 22 Aug | 25 Aug - 29 Aug | 30 Aug 3 Sept | 04 sept- 08 sept | 11 Sept - 15 Sept | 18 Sept - 22 Sept | 25 Sept- 29 Sept | 30 Sept 3 Oct | 04 Oct- 08 Oct | 11 Oct - 15 Oct | 18 Oct- 22 Oct | 25 Oct- 29Oct | 30 Oct 3 Nov | 04 Nov- 08 Nov | 11 Nov- 15 Nov | 18 NOv- 22 Nov | 25 Nov- 29 Nov | 30 Nov 3 Dec | 04 Dec - 08 Dec | 11 Dec - 15 Dec | 18 Dec - 22 Dec | 28 Dec- 31 Dec
| * Requirment Analysis | 100% | Done |  | Requirement Analysis |  |  |  | Requirement Analysis
| * Test Design | 100% | Done |  |  | Test Design |  |  |  | Test Design
| * Functional Test Execution | Not Started | [17 empty] | Test Case Execution
| * API Testing (X APIs) | Not Started | [19 empty] | API Testing
| * End to End Testing | Not Started | [17 empty] | End to End Test Execution
UAT Support
* UAT Defect Analysis
* UAT Sign Off
| Sprint 2 |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  |  | October |  |  |  |  | November |  |  |  |  | December
| Project Phase | Progress | RAG | 05 May - 09 May | 12 May - 16 May | 19 May - 23 May | 26 May - 30 May | 02 June - 06 June | 09 June - 13 June | 16 June - 20 June | 23 June - 27 June | 30 July - 04 July | 07 July - 11 July | 14 July - 18 July | 21 July - 25 July | 28 July - 01 Aug | 04 Aug - 08 Aug | 11 Aug - 15 Aug | 18 Aug - 22 Aug | 25 Aug - 29 Aug | 30 Aug 3 Sept | 04 sept- 08 sept | 11 Sept - 15 Sept | 18 Sept - 22 Sept | 25 Sept- 29 Sept | 30 Sept 3 Oct | 04 Oct- 08 Oct | 11 Oct - 15 Oct | 18 Oct- 22 Oct | 25 Oct- 29Oct | 30 Oct 3 Nov | 04 Nov- 08 Nov | 11 Nov- 15 Nov | 18 NOv- 22 Nov | 25 Nov- 29 Nov | 30 Nov 3 Dec | 04 Dec - 08 Dec | 11 Dec - 15 Dec | 18 Dec - 22 Dec | 28 Dec- 31 Dec
| * Requirment Analysis | 100% | Done |  |  | Requirement Analysis
| * Test Design | 100% | Done |  |  |  | Test Design
| * Functional Test Execution | Not Started | [18 empty] | Test Case Execution
| * API Testing (X APIs) | Not Started | [20 empty] | API Testing
| * End to End Testing | Not Started | [13 empty] | End to End Test Execution |  |  |  |  | End to End Testing
UAT Support
* UAT Defect Analysis
* UAT Sign Off
| Sprint 3 |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  |  | October |  |  |  |  | November |  |  |  |  | December
| Project Phase | Progress | RAG | 05 May - 09 May | 12 May - 16 May | 19 May - 23 May | 26 May - 30 May | 02 June - 06 June | 09 June - 13 June | 16 June - 20 June | 23 June - 27 June | 30 July - 04 July | 07 July - 11 July | 14 July - 18 July | 21 July - 25 July | 28 July - 01 Aug | 04 Aug - 08 Aug | 11 Aug - 15 Aug | 18 Aug - 22 Aug | 25 Aug - 29 Aug | 30 Aug 3 Sept | 04 sept- 08 sept | 11 Sept - 15 Sept | 18 Sept - 22 Sept | 25 Sept- 29 Sept | 30 Sept 3 Oct | 04 Oct- 08 Oct | 11 Oct - 15 Oct | 18 Oct- 22 Oct | 25 Oct- 29Oct | 30 Oct 3 Nov | 04 Nov- 08 Nov | 11 Nov- 15 Nov | 18 NOv- 22 Nov | 25 Nov- 29 Nov | 30 Nov 3 Dec | 04 Dec - 08 Dec | 11 Dec - 15 Dec | 18 Dec - 22 Dec | 28 Dec- 31 Dec
| * Requirment Analysis | 100% | Done |  |  |  | Requirement Analysis
| * Test Design | 80% | In Progress |  |  |  |  | Test Design
| * Functional Test Execution | Not Started | [22 empty] | Test Case Execution
| * API Testing (X APIs) | Not Started | [24 empty] | API Testing
| * End to End Testing | Not Started | [13 empty] | End to End Test Execution | [8 empty] | End to End Testing
UAT Support
* UAT Defect Analysis
* UAT Sign Off